CONTRACT FOR MIGRATION OF SPPA-T2000 (DCS TELEPERM XP)

TO SPPA-T3000/R3000&E3000

Between

CONTOURGLOBAL MARITSA EAST 3 AD

And

…….................

__________________________

MARITSA EAST 3

__________________

2017

TABLE OF CONTENTS

Section 1 -  LETTER OF AWARD

Section 2 -  THE AGREEMENT

Section 3 -  THE SPECIFICATION

Section 2 – THE AGREEMENT

TABLE OF CONTENT

Clause 											page

1	Definitions	3

2	Precedence of Documents	7

3	CONTRACTOR to Inform Himself	7

4	CONTRACTOR’s General Obligations	8

5	CONTRACTING AUTHORITY’s General Obligations	9

6	Programme	10

7	Drawings, Manuals and Technical Information	11

8	Inspection and Testing	13

9	Delivery	14

10	Removal of Improper Work and Materials	14

11	 Tests for Completion	14

12	Take Over	15

13	Care of the Works	16

14	Extension of the Completion Date / Physical Completion Date and Delay	17

15	Variations to and Suspension of the Works	18

16	Defects Liability Period	18

17	Final Take Over Certificate	19

18	Payment and Security	20

19	Insurance	22

20	Applicable Laws, Approvals and Other Requirements	23

21	CONTRACTOR’s Events of Default	23

22	CONTRACTING AUTHORITY’s Events of Default	25

23	Liability and Limitations on Liability	26

24	Confidentiality	26

25	Assignment and Sub-Contracting	27

26	Law, Jurisdiction, Disputes and Language	27

27	Force Majeure	29

27.1	Notification Obligations	29

27.2	 Duty to Mitigate	30

27.3	Effect of Extended Force Majeure Event	30

27.4	Effect of the Termination	30

28.	Health & Safety	30

29 	Waiver	31

30	Notices	32

31	Entire Agreement	32

32	Amendments	33

33	Ancillary provisions	33

SCHEDULES:

SCHEDULE A – CONTRACTORS COMMERCIAL OFFER

SCHEDULE B – LIST OF APPROVED SUBCONTRACTORS

SCHEDULE C – TESTS FOR COMPLETION

SCHEDULE D – MILESTONE PAYMENT SCHEDULE

SCHEDULE E – PROGRAMME

SCHEDULE F – FORMS OF PERFORMANCE GUARANTEE AND ADVANCE PAYMENT GUARANTEE

SCHEDULE G – CONTRACTORS ORGANISATIONAL CHART

SCHEDULE H - CONTRACTING AUTHORITY’S ANTICORRUPTION POLICY

SCHEDULE I - SUPPLIER CODE OF CONDUCT

SCHEDULE J - VENDOR CERTIFICATE – SANCTIONS LAWS

SCHEDULE K – AGREEMENT PROTOCOL FOR SAFETY

SCHEDULE L - BASIC PRINCIPLES FOR PROTECTION AGAINST EXPOSURE TO ASBESTOS

THIS AGREEMENT is made on ……..……. 2017

BETWEEN:

- CONTOURGLOBAL MARITSA EAST 3 AD, having its seat and registered office address in Sofia city, № 48 Sitnyakovo Blvd, 9th floor, registered in the Registry Agency under UIC 130020522, Tax number BG 130020522, represented by Krassimir Nenov – Executive Director and Quinto Di Ferdinando - Member of the Board of Directors, hereinafter referred to as CONTRACTING AUTHORITY, and

- ………………………………………………. hereinafter referred to as CONTRACTOR.

(each a “Party” and collectively the “Parties”)

WHEREAS, the CONTRACTING AUTHORITY requires the migration of of the Control system for technological processes and protections SPPA-T2000 (DCS Teleperm XP) to SPPA-T3000/R3000&E3000 at the ContourGlobal Maritsa East 3 Power Station (the “Facility”); and

WHEREAS, the CONTRACTING AUTHORITY wishes the CONTRACTOR to undertake the design, engineering, procurement, installation, testing and commissioning of said migration of SPPA-T2000; and

WHEREAS, the CONTRACTOR has experience in providing designing, engineering, procuring, installing, testing and commissioning services similar to those requested by the CONTRACTING AUTHORITY hereunder and is prepared to undertake such work.

NOW THEREFORE, in consideration of the promises contained in this Agreement, the CONTRACTING AUTHORITY and the CONTRACTOR agree as follows:

# 1	Definitions

In construing this Agreement (as hereinafter defined) the following words and expressions shall have the meanings hereby assigned to them:-

“Advance Payment” 			means the payment in the amount of ………… to be made by the CONTRACTING AUTHORITY to the CONTRACTOR pursuant to Clause 18.2 of this Agreement

“Advance Payment Guarantee”                has the meaning as set forth in Clause 18.3 hereto.

“Agreement” 				means this agreement between the CONTRACTING AUTHORITY and the CONTRACTOR for the execution of the Works and all documents included in, annexed to or incorporated by reference into this agreement.

“Applicable Laws” 			means any statute, law, directive, by-law, regulation, rule, order or other legislation of any Competent Authority applicable to the performance of the Works or the operation or use of the Facility.

“Approvals” 				means all permits, licenses, approvals, consents and any other form or authorisation required from any Competent Authority to be obtained and maintained in connection with the performance of the Works or the operation or use of the Facility.

“CONTRACTING AUTHORITY” 	means CONTOURGLOBAL MARITSA EAST 3 AD and includes the CONTRACTING AUTHORITY’s legal representatives, successors and assigns.

“Commencement Date” 		means the date specified in the Letter of Award as the date for the commencement of the Works.

“Competent Authority” 		means any legislative, judicial, regulatory or administrative body of the Republic of Bulgaria or any other national or municipal body or other instrumentality of the Republic of Bulgaria that has authority to bind a person in law or whose directives, decisions, instructions, rulings, laws or regulations are directly enforceable against the CONTRACTOR or the CONTRACTING AUTHORITY.

"Completion" 				means the point at which the Works have successfully passed the Tests for Completion and have been certified by the CONTRACTING AUTHORITY as complete, in accordance with the Agreement and the Acceptance Criteria set out in Section 3 and a Take Over Certificate is issued by the CONTRACTING AUTHORITY to the CONTRACTOR.  The term “Completed” shall be construed accordingly.

“Completion Date” 			means the date when the Works have to be Completed, including the Tests for Completion and the Works are taken over which has been agreed to be …… days after Physical Completion Date. The Parties will agree different Completion Dates for the respective portions of the Works as described in the Specification.

"Contract Price" 			means the sum of …………………........ as the price payable pursuant to Clause 18.1 by the CONTRACTING AUTHORITY to the CONTRACTOR for the execution of the Works.

"CONTRACTOR" 			means ………………… and includes the CONTRACTOR's legal representatives, successors and assigns.

“CONTRACTOR's Equipment” 	means all appliances or things of whatsoever nature required for the purposes of the Works but does not include materials or other things intended to form or forming part of the Works.

“Defects Liability Period” 		has the meaning set forth in Clause 16.1.

“Facility” 				means the ContourGlobal Maritsa East 3 Power Station.

“Final Take Over” 			means the date on which the CONTRACTING AUTHORITY certifies that the Punchlist Items have been completed or any extension thereof has expired.  The term “Final Taking Over” shall be construed accordingly.

“Final Take Over Certificate” 	means a formal written Notice from the CONTRACTING AUTHORITY to the CONTRACTOR confirming the date on which Final Take Over occurred.

“Good Industry Practice” 		means the exercise of that degree of skill, diligence, prudence and construction practice which would reasonably be expected from a skilled and experienced CONTRACTOR carrying out work of the same type as the Works under the same or similar circumstances.

“Longstop Completion Date” 	means date occurring 60 calendar days after the Completion Date.

“Milestone”				means the activity set out in the Schedule D (Milestone Payment Schedule) to this Agreement

“Performance Guarantee		has the meaning set forth in Clause 18.9.

“Physical Completion Date” 		means 5 (five) calendar days before the Planned Synchronization Date, being the date when the Works have to be completed save for the Tests for Completion. It is understood that as of that date the Works will be in a position to allow the operation of the Facility to the reasonable satisfaction to the CONTRACTING AUTHORITY and as certified by him in a Certificate for Physical Completion.

“Planned Outage Schedule”		means the Facility outage schedule agreed in advance between the CONTRACTING AUTHORITY and his counterparties under the power purchase agreement and grid connection agreement for the performance of planned maintenance works on the Facility by the CONTRACTING AUTHORITY.

“Planned Synchronization Date”	means each date for synchronization of the respective unit of the Facility as provided by the CONTRACTING AUTHORITY in accordance with the agreed Planned Outage Schedule for the Facility.

“Programme” 				has the meaning set forth in Clause 6.2.

“Punchlist” 				means a list agreed to by the CONTRACTING AUTHORITY, at the time of Completion, of outstanding items of a minor nature, the non-completion of which does not affect the safe, reliable operation of the Works or any component of the Facility.

“Site” 					means the site on which the Facility is located and the actual place to where the Works are to be executed or carried out, together with so much of the area surrounding said place as the CONTRACTOR shall actually use in connection with the Works otherwise than merely for the purpose of access to said place.

“Specification” 			means the specification of the Works annexed to or included in this Agreement.

“SUBCONTRACTOR” 		means any person (other than the CONTRACTOR) to whom any part of this Agreement has been sub-contracted with the consent in writing of the CONTRACTING AUTHORITY, and the legal representatives and successors of such person.

“Take Over” 				means the date on which the CONTRACTING AUTHORITY certifies that the Works have been Completed (except in respect of minor defects listed on the Punchlist).  The terms “Taken Over” and “Taking Over” shall be construed accordingly.

“Take Over Certificate” 		means a formal written Notice from the CONTRACTING AUTHORITY to the CONTRACTOR confirming the Completion date.

"Tests for Completion" 		means those tests agreed between the CONTRACTOR and the CONTRACTING AUTHORITY to determine whether the Works have achieved Completion.

"Works" 				means all materials, documents, services and other things of all kind to be furnished by the CONTRACTOR and its SUBCONTRACTOS and vendors, or that may be required to design, engineer, procure, install, test and commission the said migration of SPPA-T2000, in accordance with this Contract and its Schedules.

# 2	Precedence of Documents

The several documents forming this Agreement are to be taken as mutually explanatory of one another. In the case of any ambiguity, inconsistency, discrepancy or conflict, this Agreement shall take precedence over the Schedules and the Schedules shall take precedence over the other documents forming part of this Agreement.

# 3	CONTRACTOR to Inform Himself

3.1	The CONTRACTOR shall be deemed to have inspected the Site and to have satisfied himself as far as can reasonably be done as to the nature, environment and other conditions of the Site and all circumstances affecting the Site (including any safety regulations of the CONTRACTING AUTHORITY applicable thereto) and as to the feasibility of executing the Works in accordance with the terms and conditions of this Agreement. Subject to the express provisions of this Agreement the cost of executing and completing the Works, and any costs associated with the CONTRACTOR’s Equipment, shall be borne by the CONTRACTOR who shall be deemed to have obtained all information and taken into account all circumstances which may affect such cost. It is understood that the CONTRACTOR is familiar with the Bulgarian and international legislation with respect to design, engineering, delivery, installation, testing and commissioning of projects similar to the Works.

3.2	The Contract Price shall be a fixed price lump sum amount for the fully completed Works. The Contract Price shall not be subject to increase for any reason except in accordance with Clauses 15.2, 15.3, 20.3 of this Agreement.

# 4	CONTRACTOR’s General Obligations

  - The CONTRACTOR shall design, engineer, manufacture, supply, install, complete and commission the Works as set out in the Specification and successfully carry out the Test of Completion in respect with the Works within the Completion Date. The CONTRACTOR shall also make good defects in the Works, and damage resulting therefrom, in accordance with the Agreement.

  - The CONTRACTOR shall produce and present to the CONTRACTING AUTHORITY  all necessary documents confirming the quality of the supplied equipment and completed works, including but not limited to acts, protocols, certificates, declarations of conformity, permits, completion certificates, testing certificates, and any other document reasonably requested by the CONTRACTING AUTHORITY or the  Consultant as required by Bulgarian regulations.

4.3	The CONTRACTOR shall, subject to the provisions of this Contract, complete the Works and any variation or addition thereto authorised by the CONTRACTING AUTHORITY with due care and diligence and execute the Works prior to the Completion Date. The CONTRACTOR shall provide all materials, supplies, labour, personnel, all CONTRACTOR's Equipment and all other things whether of a temporary or permanent nature required for the execution of the Works.

4.4	The CONTRACTOR shall be responsible for maintaining the CONTRACTOR's Equipment on Site in safe working order. The CONTRACTOR shall be liable for loss of or damage to any of the CONTRACTOR's Equipment which may occur otherwise than through the default of the CONTRACTING AUTHORITY or those for whom he is responsible.

4.5	If this Agreement is terminated under Clause 21 the CONTRACTING AUTHORITY shall have the use of any of the CONTRACTOR’s Equipment for the time being on Site. The PARTIES shall settle their financial relations with regard to the use of the CONTRACTOR’s Equipment via separate Agreement.

4.6	The CONTRACTOR shall be responsible for the adequacy, stability and safety of its operations on Site especially such matters as concern the safety, health and welfare of persons on or adjacent to the Site or within the area in which the Works are being carried out. In addition, the CONTRACTOR shall also comply with, and shall cause its SUBCONTRACTORS to comply with, the safety rules of the CONTRACTING AUTHORITY pertaining to the Site, together with permits to work, codes of practice and in particular such matters as concern the safety, health and welfare of persons working on the Site.

4.7	The Works shall be executed in accordance with Good Industry Practice and in the manner set out in Specification or, where not so set out, to the reasonable satisfaction of the CONTRACTING AUTHORITY and all work on Site shall be carried out in accordance with such reasonable directions as the CONTRACTING AUTHORITY may give.

4.8	In the performance of the Works the CONTRACTOR shall take all prudent and reasonable steps and use Good Industry Practice to protect against any damage to the Works, the Facility, and any equipment belonging to the Facility which it has been permitted to use.

4.9	The CONTRACTOR acknowledges that while the CONTRACTOR is performing the Works on Site, the CONTRACTING AUTHORITY’s operation of the Facility shall be restricted only upon agreement in writing in advance with regard to the timing, the extent and the term of the restriction as per Attachment to the Specification.

4.10	The CONTRACTOR shall maintain the Site in a clean, tidy and safe manner and free from the accumulation of waste from the performance of the Works.

4.11	The CONTRACTOR shall employ one competent representative whose names shall have been notified previously to the CONTRACTING AUTHORITY by the CONTRACTOR (the “CONTRACTOR’s Representative“ to manage and supervise the carrying out of the Works on the Site. The CONTRACTOR’s Representative shall be present on the Site during working hours, and any orders or instructions which the CONTRACTING AUTHORITY may give to the CONTRACTOR’s Representative shall be deemed to have been given to the CONTRACTOR. The CONTRACTING AUTHORITY shall be entitled by notice to the CONTRACTOR to object to any representative or person employed by the CONTRACTOR in the execution of or otherwise about the Works who shall, in the reasonable opinion of the CONTRACTING AUTHORITY, misconduct himself or be incompetent or negligent, and the CONTRACTOR shall remove such person from the Works. The language of communication shall be English and Bulgarian. CONTRACTOR shall provide at signing of this Agreement organigram and CV of CONTRACTOR’s Representative which is appended hereto as Schedule G.

4.12 	Training of the CONTRACTING AUTHORITY’s personnel and the other persons nominated by the CONTRACTING AUTHORITY shall be given by the CONTRACTOR as required by the Specification.

# 5	CONTRACTING AUTHORITY’s General Obligations

5.1	The CONTRACTING AUTHORITY shall allow the CONTRACTOR (and its employees, nominees, agents and SUBCONTRACTORS) all reasonable access to the Site and the Facility as may be required by the CONTRACTOR (and its employees, nominees, agents and SUBCONTRACTORS) in connection with, or ancillary to, the performance of the Works as from the Commencement date.  However, the CONTRACTING AUTHORITY shall not be bound to give the CONTRACTOR exclusive access to or control of any part of the Site.

5.2	The CONTRACTING AUTHORITY shall employ one competent representative, whose name shall have been notified previously to the CONTRACTOR by the CONTRACTING AUTHORITY (the “CONTRACTING AUTHORITY’s Representative”), to oversee the carrying out of the Works on the Site.  The CONTRACTING AUTHORITY’s Representative or his Deputy shall be present on the Site during normal working hours, and any communications which the CONTRACTOR shall make to the CONTRACTING AUTHORITY’s Representative shall be deemed to have been given to the CONTRACTING AUTHORITY.  The CONTRACTING AUTHORITY may at any time with prior written notice to the CONTRACTOR change the CONTRACTING AUTHORITY’s Representative.

5.3 	The CONTRACTING AUTHORITY shall make available to the CONTRACTOR access to its disposal site for the waste.

# 6	Programme

  - The CONTRACTOR and the CONTRACTING AUTHORITY have agreed a schedule for execution of the Works appended to the Agreement as Schedule E.

  - The CONTRACTOR shall submit to the CONTRACTING AUTHORITY not later than 30 days after Commencement Dated a programme (the “Programme”) in a form of a computer based project management system to be able to monitor the process for the execution of the Works in accordance with the requirements of the Specification and showing:

- the sequence and timing of the activities by which the CONTRACTOR proposes to carry out the (including design, manufacture, delivery to Site, installation, commissioning and testing) which sequence must be in accordance with the sequence  of the  Works as set out in the Specification;

- the anticipated numbers of skilled and unskilled labour and supervisory staff required for the various activities when the CONTRACTOR is working on Site;

- the respective times for submission by the CONTRACTOR of Drawings, Manuals and Technical Information Drawings for the approval thereof by the CONTRACTING AUTHORITY.

6.3	The CONTRACTOR shall not, without the prior written approval of the CONTRACTING AUTHORITY, make any material alteration to the Programme.

6.4	The CONTRACTING AUTHORITY and the CONTRACTOR shall co-operate with each other and co-ordinate the scheduling of work and activities so as to cause the minimum disturbance to the normal operation of the Facility and to the progress of the Works.

6.5 	The CONTRACTOR shall be required, when requested by the CONTRACTING AUTHORITY, to attend progress review and/or co-ordination meetings where progress of the Works together with issues relating to progress shall be reviewed and the CONTRACTOR shall provide the CONTRACTING AUTHORITY such information relating to progress, resources, productivity, purchasing etc. as the CONTRACTING AUTHORITY requires to enable adequate review to be carried out and to monitor the progress of the Works.

# 7	Drawings, Manuals and Technical Information

7.1 	The CONTRACTOR shall provide full design documentation – drawings, explanatory notes, calculations, specifications, technical information, etc. in accordance with the requirements of the CONTRACTING AUTHORITY in accordance with the Agreement and the Bulgarian law and shall present to the CONTRACTING AUTHORITY  3 /three/ hard copies and 1 /one/ soft copy on CD for review and approval within the term specified in the approved schedule or if such term is not specified within a reasonable period of time. The design documentation has to comply with the requirement of the Bulgarian and EU norms and requirements to the design documentation. In case of discrepancies between these requirements the CONTRACTOR shall comply with the stricter requirements.

Following completion of the Works but before the Final Take Over certificate the CONTRACTOR shall present to the CONTRACTING AUTHORITY  3 /three/ hard copies and 1 / one/ soft copy on CD of the complete as-built documentation – drawings, explanatory notes, calculations, specifications, technical information, etc. compliant in form and substance with the requirements of the CONTRACTING AUTHORITY.

7.2	The CONTRACTOR shall present to the CONTRACTING AUTHORITY all required documents confirming the quality of the supplied equipment and completed works, including but not limited to acts, protocols, certificates, declarations of conformity, permits, completion certificates, testing certificates, and any other document reasonably requested by the CONTRACTING AUTHORITY in accordance with the Agreement and the Bulgarian law.  The approval of all drawings and documentation does not release the CONTRACTOR from its obligation to fulfill all Works under this Agreement.

7.3	The CONTRACTOR shall be responsible for ensuring all drawings and documents are in such form as is necessary for the CONTRACTING AUTHORITY to comply with any Applicable Law or Approvals. The CONTRACTING AUTHORITY shall have 10 days for approval of drawings submitted by the CONTRACTOR.

7.4	The CONTRACTOR shall modify any drawings of which the CONTRACTING AUTHORITY disapproves in writing so as to comply with his comments and requirements in accordance with the Agreement and the Bulgarian law, and shall re-submit such drawings for his approval without delay.

7.5	The CONTRACTOR shall submit to the CONTRACTING AUTHORITY for inspection and approval within the time specified in the approved Programme, or if no time is specified then a reasonable time 3 copies of drafts of the operating and maintenance manuals for the Works. The CONTRACTOR shall modify any manuals, of which the CONTRACTING AUTHORITY disapproves, so as to comply with his comments and requirements in accordance with the Agreement and the Bulgarian law, and shall re-submit such manuals for his approval without delay.

7.6	Before the Works are Taken Over the CONTRACTOR shall supply 3 copies of the modified draft operation and maintenance manuals.  Take Over of the Works cannot occur until such draft manuals and drawings have been supplied.

7.7	Notwithstanding any approval or inspection by the CONTRACTING AUTHORITY of any of the documentation provided for in this Clause 7, the CONTRACTOR shall be responsible for any failure thereof to comply with or achieve the requirements of the Works and for any errors, omissions or discrepancies contained therein.  The CONTRACTOR shall bear any costs he may incur as a result of delay in providing the documentation or as a result of errors, omissions or discrepancies therein, for which the CONTRACTOR is responsible in accordance with the Agreement and the Bulgarian law.  The CONTRACTOR shall also at his own expense carry out, or bear the reasonable cost of, any alterations or remedial work made necessary by such errors, omissions or discrepancies for which he is responsible and modify the documentation accordingly.

  - The CONTRACTOR shall indemnify the CONTRACTING AUTHORITY from and against all actions, claims, costs and procedures for or on account of infringement or alleged infringement of any patent rights design trade-mark or name or other protected rights in respect of the structural and detailed design of the Works and against all claims demands proceedings damages costs charges and expenses whatsoever in respect thereof or in relation thereto.

  - The CONTRACTOR shall present all Drawings, Manuals and Technical Information and all other documentation required for the proper execution and approval of the Works in both Bulgarian and English language.

# 8	Inspection and Testing

8.1	The CONTRACTING AUTHORITY shall be entitled at all reasonable times during manufacture to inspect, examine, and test on the CONTRACTOR’s premises the materials and workmanship and performances of all Works, and if part of the Works is being manufactured on other premises the CONTRACTOR shall obtain for the CONTRACTING AUTHORITY permission to inspect, examine, and test as if the Plant were being manufactured on the CONTRACTOR’s premises.  Such inspection, examination or testing shall not release the CONTRACTOR from any obligation under this Agreement.

8.2	The CONTRACTOR shall, after consulting the CONTRACTING AUTHORITY, give the CONTRACTING AUTHORITY reasonable notice in writing of the date on and place at which the Works or any part thereof will be ready for testing or inspection as per the Specification or the Tests for Completion, as appropriate, and unless the CONTRACTING AUTHORITY shall attend at the place so named on the date which the CONTRACTOR has stated in his notice the CONTRACTOR may proceed with the tests or inspections, which shall be deemed to have been made in the CONTRACTING AUTHORITY’s presence, and shall forthwith forward to the CONTRACTING AUTHORITY duly certified copies of the test or inspection report. The CONTRACTING AUTHORITY shall give the CONTRACTOR 24 hours notice in writing of his intention to attend the tests.

8.3	Where the Specification or the Tests for Completion, as appropriate, provides for tests on the premises of the CONTRACTOR or of any SUBCONTRACTOR the CONTRACTOR, except where otherwise specified, shall provide free of charge such assistance, labour, materials, electricity, fuel, stores, apparatus and instruments as may be required and as may be reasonably demanded to carry out such tests efficiently.

8.4 	Where the Specification or the Tests for Completion, as appropriate, provides for tests on the Site the CONTRACTING AUTHORITY, except where otherwise specified, shall provide free of charge, such labour, materials, electricity, fuel, stores and apparatus, as may be required and as may be reasonably demanded to carry out such tests efficiently.

8.5 	As and when the CONTRACTING AUTHORITY is satisfied that any Works shall have passed the tests referred to in this clause he shall notify the CONTRACTOR in writing to that effect.

8.6 	If after inspecting, examining, or testing any Works the CONTRACTING AUTHORITY shall decide that such Works or any part thereof is defective or not in accordance with this Agreement, he may reject such Works or part thereof by giving to the CONTRACTOR within a reasonable time notice in writing of such rejection, stating therein the grounds upon which the said decision is based.

8.7	The CONTRACTOR and the CONTRACTING AUTHORITY shall have the right to inspect the progress of the Works and shall have access to any SUBCONTRACTOR performing the Works.  Each of the parties shall perform such inspections in such manner and at such time as it considers appropriate to the relevant stage of the Works in order to ensure that the Works conform to, and are being performed in accordance with the terms of this Agreement.

# 9	Delivery

The CONTRACTOR shall notify the CONTRACTING AUTHORITY 7 days in advance for any deliveries of materials or CONTRACTOR's Equipment to the Site.

The CONTRACTOR shall be responsible for the reception and unloading of all materials and CONTRACTOR's Equipment delivered to the Site for the purposes of this Agreement.

# 10	Removal of Improper Work and Materials

10.1	The CONTRACTING AUTHORITY shall during the progress of the Works have power to instruct in writing:

(a)	the removal from the Site within such time or times as may be specified in the order of any materials which in the reasonable opinion of the CONTRACTING AUTHORITY are not in accordance with this Agreement  and/or

(b)	the substitution of proper and suitable materials; and/or

(c)	the removal and proper re-execution (notwithstanding any previous test thereof) of any work which in respect of materials or workmanship is not in the reasonable opinion of the CONTRACTING AUTHORITY in accordance with this Agreement.

# 11		Tests for Completion

11.1	The CONTRACTOR shall give to the CONTRACTING AUTHORITY in writing 2 days’ notice of the date after which he will be ready to perform the Tests for Completion.  Unless otherwise agreed the Tests for Completion shall take place within 10 days of the date notified, on such day or days as the CONTRACTING AUTHORITY shall in writing notify the CONTRACTOR. For avoidance of doubt the Tests for Completion may be done after the Physical Completion Date.

11.2	If the CONTRACTING AUTHORITY is unable to facilitate the Tests for Completion, after having been duly notified of them by the CONTRACTOR pursuant to Clause 11.1, the CONTRACTOR shall reschedule such Tests for Completion for the earliest date when the CONTRACTING AUTHORITY is able to facilitate the Tests, but which shall not be more than 10 days from the original date scheduled for the Tests for Completion. If the CONTRACTING AUTHORITY fails to arrange for such rescheduling of the Tests for Completion, the CONTRACTOR shall be entitled to an extension to the time for Completion of the Agreement. The CONTRACTOR shall be reimbursed for all reasonable expenses he may incur as a result of the delay of the Test for Completion.

11.3	If the Tests for Completion are being unduly delayed, the CONTRACTING AUTHORITY may by notice in writing call upon the CONTRACTOR to perform such Tests for Completion within 6 (six) days from the receipt of such notice. If the CONTRACTOR fails to perform the Tests for Completion within such time the CONTRACTING AUTHORITY shall himself proceed with the Tests for Completion. All Tests for Completion performed by the CONTRACTING AUTHORITY shall be at the risk and expense of the CONTRACTOR unless the CONTRACTING AUTHORITY acts against the clear recommendations of the CONTRACTOR which however shall not endanger the health and safety of any personal or machinery and the CONTRACTOR shall establish that the Tests for Completion were not being unduly delayed in which case those Tests for Completion shall be at the risk and expense of the CONTRACTING AUTHORITY.

11.4	If any section or portion of the Works fails to pass the Tests for Completion upon CONTRACTOR’s default, tests of such section or portion shall, if required by the CONTRACTING AUTHORITY, be repeated within a reasonable time upon the same terms and conditions, except that all reasonable expenses which the CONTRACTING AUTHORITY may incur as a result of the repetition of the Tests for Completion shall be deducted from the Contract Price.

  - During the Tests for Completion the CONTRACTING AUTHORITY shall make available such number of the Facility’s operating and maintenance personnel as the CONTRACTOR may from time to time reasonably require in order to perform normal operation and maintenance duties in connection with the testing of the Works. The CONTRACTING AUTHORITY and the CONTRACTOR shall co-ordinate the scheduling of the Tests for Completion so as to cause minimum disturbance to the normal operation of the Facility.

  - During the Tests on Completion the CONTRACTING AUTHORITY’s operating personnel will act under the supervision of the CONTRACTOR. The CONTRACTOR shall be entirely responsible for the operation of the Works.

# 12	Take Over

12.1	When the CONTRACTOR considers the Works have been Completed in accordance with this Agreement and its Schedules (except for the Punchlist items and except as provided in Clause 16) and all documents required under related legislation for the completed Works and have passed the Tests for Completion it shall apply to the CONTRACTING AUTHORITY for the issuance and of a Take Over Certificate. The agreed by the CONTRACTING AUTHORITY Punchlist shall be attached to the Take Over Certificate.

12.2	Within 15 days of the CONTRACTING AUTHORITY having received the application for the Take Over Certificate submitted by the CONTRACTOR in accordance with Clause 12.1, the CONTRACTING AUTHORITY shall either confirm the Works have achieved Completion by issuing the Take Over or advise the CONTRACTOR of any work to be performed for the Works to achieve Completion.  If the CONTRACTING AUTHORITY advises the CONTRACTOR that there is remaining work to be performed to achieve Completion, the CONTRACTOR shall perform all such work. Upon completion of any remaining work advised by the CONTRACTING AUTHORITY to the CONTRACTOR, the CONTRACTOR shall submit a fresh application for a Take Over Certificate.  The aforementioned procedure shall be repeated until the CONTRACTING AUTHORITY signs the Take Over Certificate. The CONTRACTING AUTHORITY shall be deemed to have Taken-Over the Works on the date so certified.

12.3	If by reason of any default on the part of the CONTRACTOR the Take Over Certificate has not been issued in respect of every section or portion of the Works within one month of the Completion Date, the CONTRACTING AUTHORITY shall be entitled to use the Works or any section or portion thereof in respect of which the Take Over Certificate has not been issued if and so long as the Works or the section or portion to be used is reasonably capable of being used.

12.4	The CONTRACTOR shall execute all works included in the Punchlist in the term specified in the agreed schedule.  The completion of these works shall be certified by the CONTRACTING AUTHORITY by issuance of a Final Taking Over Certificate.

# 13	Care of the Works

13.1		The CONTRACTOR shall have care, custody and control of the Works or any section thereof from the Commencement Date until the Works are Taken Over.  The CONTRACTOR shall also be responsible for the care of any part of the Works upon which any outstanding work is being performed by the CONTRACTOR until the completion of such work.  Loss of or damage to the Works or any section thereof occurring prior to Take Over and arising from any cause whatsoever other than any intentional or gross negligent act or omission of the CONTRACTING AUTHORITY shall be made good forthwith by the CONTRACTOR at his own cost.  After Take Over the CONTRACTOR’s liability in respect to loss of or damage to any part of the Works shall be limited to the fulfilment of the CONTRACTOR’s liability for defects and to making good loss or damage caused by the defects or the CONTRACTOR during the Defects Liability Period in accordance with Clause 16.

13.2	 Notwithstanding the foregoing, the Works supplied pursuant to this Agreement shall become the property of the CONTRACTING AUTHORITY when delivered to Site pursuant to this Agreement.

13.3		The CONTRACTOR shall indemnify and hold harmless the CONTRACTING AUTHORITY against any claims, losses or damage arising from any defect in title or encumbrance or charge upon any Plant supplied pursuant to this Agreement.

# 14	Extension of the Completion Date / Physical Completion Date and Delay

14.1	If, by reason of any variation ordered pursuant to Clause 15, any breach of this Agreement by the CONTRACTING AUTHORITY, or an event of Force Majeure as set forth in Clause 27, the CONTRACTOR shall have been delayed in the completion of the Works, then provided that the CONTRACTOR shall as soon as reasonably practicable but in any case not later than 5 days after happening of the relevant event,  have given to the CONTRACTING AUTHORITY notice of his claim for an extension of time with full supporting details, the CONTRACTING AUTHORITY shall on receipt of such notice grant the CONTRACTOR from time to time in writing either prospectively or retrospectively an extension of the Completion Date as he considers to be reasonable.

14.2	It is a condition precedent to the CONTRACTOR's entitlement to an extension of the Completion Date under Clause 14.1 above, that he shall, in the opinion of the CONTRACTING AUTHORITY, have taken all reasonable steps to mitigate the consequences of the actual or anticipated delay.

14.3	If the CONTRACTOR finds that he will be unable to complete the Works by the Completion Date or if such a delay on his part is likely, he shall immediately notify the CONTRACTING AUTHORITY of this delay stating the reason for the delay, the steps being taken to overcome or mitigate such delay and, if possible, the date on which Taking Over of the Works may be expected.

  - If the CONTRACTOR fails to achieve Physical Completion Date or Take Over on or before the Completion Date, including successful passing of the Test on Completion, there shall be deducted from the Contract Price or paid to the CONTRACTING AUTHORITY by the CONTRACTOR an amount of Eur 15,000 (fifteen thousand Euros) per day, for each day of delay.

  - If the CONTRACTOR fails to achieve Take Over in accordance with this Agreement on or before the Longstop Completion Date, the CONTRACTING AUTHORITY may by notice require the CONTRACTOR to complete the Works within 7 days of receipt of such notice by the CONTRACTOR. If the CONTRACTOR fails to complete the Works within such time, and this is not due to a cause for which the CONTRACTING AUTHORITY is responsible, the CONTRACTING AUTHORITY may by further notice to the CONTRACTOR either:

- require the CONTRACTOR to complete the Works within a reasonable time (being not more than 30 additional calendar days), or

- terminate this Agreement and by itself or by others complete the Works.  In such case the CONTRACTING AUTHORITY shall be entitled to recover from the CONTRACTOR any reasonable excess cost or loss suffered by the CONTRACTING AUTHORITY in completing the Works as a result of the failure of the CONTRACTOR. The provisions of Clause 21.1 of the Agreement shall apply.

# 15	Variations to and Suspension of the Works

15.1	The CONTRACTOR shall not alter any of the Works except as directed in writing by the CONTRACTING AUTHORITY.  The CONTRACTING AUTHORITY may order the CONTRACTOR to amend, omit, add to or otherwise vary any of the Works and no such variation shall in any way vitiate or invalidate this Agreement. The CONTRACTOR shall carry out such variations and be bound by this Agreement in so doing as though the variations were stated herein.  Extension of time to be agreed in case the CONTRACTING AUTHORITY requests a variation provided the variations affects critical path.

15.2	The value (if any) of all such variations shall be taken into account in ascertaining the amount of the Contract Price.  The amount (if any) to be added to or deducted from the Contract Price shall be determined using reasonable rates agreed between the CONTRACTING AUTHORITY and the CONTRACTOR.

15.3	The CONTRACTING AUTHORITY may at any time by notice in writing to the CONTRACTOR suspend the performance of the Works. The CONTRACTOR shall forthwith comply with the CONTRACTING AUTHORITY’s notice and the extra demonstrable costs incurred by the CONTRACTOR in complying with such notice shall be added to the Contract Price.

15.4	The CONTRACTING AUTHORITY shall have the right to stop the Works in case it observes material deviations which in accordance with the Applicable Laws determine such action.  In this case all costs related to this interruption shall be borne by the CONTRACTOR.

# 16	Defects Liability Period

16.1 	In this Agreement the expression “Defects Liability Period” means the period commencing on the date the Works were Taken Over and expiring upon the date that is ………. months following the date of the Take Over Certificate.

16.2	If any defect or fault shall occur within the respective Defects Liability Period and shall be due to any defect in design, materials or workmanship not being in accordance with this Agreement the same, and any resulting damage, shall be made good by the CONTRACTOR at his own cost promptly after his having received from the CONTRACTING AUTHORITY written notification thereof.

16.3	If the CONTRACTOR repairs or replaces any part of the Works pursuant to this Clause 16, the provisions of this clause shall apply to the part of the Works so repaired or replaced until the expiration of a period of 18 months from the date of repair or replacement, but not earlier than the expiry date in Clause 16.1.

16.4	If any such defect or damage is not remedied within a reasonable time, the CONTRACTING AUTHORITY may proceed to do the work at the CONTRACTOR’s expense provided that he does so in a reasonable manner and notifies the CONTRACTOR of his intention to do so. The costs reasonably incurred by the CONTRACTING AUTHORITY shall be deducted from the Contract Price or be paid by the CONTRACTOR to the CONTRACTING AUTHORITY.  In such circumstances the CONTRACTOR shall not be relieved of any of his other obligations under this Agreement.

16.5	     Until the expiration of the Defects Liability Period, the CONTRACTOR shall have reasonable access at all reasonable working hours, at his own risk and expense, by himself or his duly authorised representatives, to those parts of the Works which are necessary for the CONTRACTOR to perform his obligations under this Clause 16; provided, however, that the CONTRACTOR shall first have notified the CONTRACTING AUTHORITY in writing of the programme for repairing or replacing any defective parts and the names of those individuals who shall be performing the work.

# 17	Final Take Over Certificate

17.1	Within 30 days of the date on which the Works are Taken Over the CONTRACTOR shall complete the items on the Punchlist. The CONTRACTOR shall complete the Punchlist items without interfering with the commercial operation of the Facility.

17.2	When the CONTRACTOR believes it has completed the Punchlist items or any extension thereof it shall apply to the CONTRACTING AUTHORITY for the Final Take Over Certificate, in which he shall certify the date on which he believes Final Take Over has occurred.

17.3	The CONTRACTOR shall not be entitled to apply for a Final Take Over Certificate until he has cleared away and removed from the Site all surplus materials, and temporary works of every kind, and the whole of the Site and the Works are in a clean and workmanlike condition to the satisfaction of the CONTRACTING AUTHORITY.

  - Within 15 days of the CONTRACTING AUTHORITY having received the application for the Final Take Over Certificate submitted by the CONTRACTOR in accordance with Clause 17.2, the CONTRACTING AUTHORITY shall either confirm Final Take Over has occurred by issuing the Final Take Over Certificate or advise in writing the CONTRACTOR of any work to be performed in order for Final Take Over to have occurred. If the CONTRACTING AUTHORITY advises the CONTRACTOR that there is remaining work to be performed to achieve Final Take Over the CONTRACTOR shall perform all such work. Upon completion of any remaining work advised by the CONTRACTING AUTHORITY to the CONTRACTOR, the CONTRACTOR shall submit a fresh application for a Final Take Over Certificate.  The aforementioned procedure shall be repeated until the CONTRACTING AUTHORITY has issued the Final Take Over Certificate.

# 18	Payment and Security

18.1	The CONTRACTING AUTHORITY shall pay the CONTRACTOR in consideration of the execution and completion of the Works and the remedying of defects therein the Contract Price or such other sum as may become payable under the provisions of this Agreement at the times and in the manner prescribed by this Agreement.

18.2 	The CONTRACTING AUTHORITY shall pay to the CONTRACTOR the Advance Payment within 30 days after the CONTRACTING AUTHORITY receives an Advance Payment Guarantee in a form of a bank guarantee or monetary deposit, or an insurance securing performance by covering the liability of the CONTRACTOR.  The remainder of the Contract Price shall be paid by reference to the achievement of Milestones.

18.3   At signing of the agreement the CONTRACTOR shall provide the CONTRACTING AUTHORITY with an Advance Payment Guarantee in the form as per Clause 18.2. If the Advance Payment Guarantee is in the form of a bank guarantee, it shall be in the form attached hereto in Schedule F issued by a bank acceptable to the CONTRACTING AUTHORITY and shall procure that the same remains in force until release as permitted by this Clause 18.3.

- The Advance Payment Guarantee shall be in an amount of the Advance Payment;

- It shall become effective only upon receiving unconditional deposit in the amount of the Advance Payment on the account of the CONTRACTOR;

- The amount of this guarantee shall be subject to automatically reduction in proportion to the accepted part of the works effected by the CONTRACTOR;

- The Advance Payment Guarantee shall expire on …………..;

- If the Advance Payment Guarantee is in the form of insurance, the CONTRACTOR shall furnish the CONTRACTING AUTHORITY with an original copy of an insurance policy issued for the benefit of the CONTRACTING AUTHORITY or which specifies the CONTRACTING AUTHORITY as a third benefit recipient /beneficiary.

- Any costs related to the signing of the bank guarantee or the insurance contract and maintaining their effectiveness for the required period, as well as to any payment of fees, insurance compensation for the benefit of the CONTRACTING AUTHORITY or any other expenses, shall be at the CONTRACTOR’s expense.

18.3	The CONTRACTOR shall be entitled to submit an application for a Milestone certificate upon achievement of each of the Milestones identified in Schedule D.  The CONTRACTING AUTHORITY shall have 7 days from the receipt of the application for the milestone certificate to verify that the milestone has been achieved. The CONTRACTING AUTHORITY shall make payment to the CONTRACTOR of the amount specified in the invoice for the respective Milestone, by wire transfer to the account identified in writing by the CONTRACTOR to the CONTRACTING AUTHORITY no later than 30 days following the receipt of a properly submitted invoice.

18.4	The Contract Price is deemed to exclude Value Added Tax (VAT).  To the extent that VAT is properly payable on the supply to the CONTRACTING AUTHORITY of any goods or services provided by the CONTRACTOR under this Agreement, the CONTRACTING AUTHORITY shall pay such VAT as an addition to payments otherwise due to the CONTRACTOR under this Agreement.

18.5	If payment of any sum payable under Clause 18.2 shall be unreasonably delayed by the CONTRACTING AUTHORITY, the CONTRACTOR shall be entitled to receive interest on the amount unpaid during the period of delay.  The interest shall be at the rate of 0,1% per cent per day, but not more than 20% of the contract price.

18.6	Where payment under Clause 18.3 is to differ from that invoiced, or the CONTRACTING AUTHORITY is to withhold payment of a sum due under the Agreement, the CONTRACTING AUTHORITY shall notify the CONTRACTOR in writing of the amount proposed to be withheld and the ground for withholding payment or if there is more than one ground each ground and the amount attributable to it.

18.7	At signing of this Agreement the CONTRACTOR shall provide the CONTRACTING AUTHORITY with a Performance Guarantee in the form of a bank guarantee or monetary deposit, or an insurance securing performance by covering the liability of the CONTRACTOR, and shall procure that the same remains in force until release as permitted by this Clause 18.7.

- If the Performance Guarantee is in the form of a bank guarantee, it shall be in the form attached hereto in Schedule F and issued by a bank acceptable to the CONTRACTING AUTHORITY.

- If the Performance Guarantee is in the form of insurance, the CONTRACTOR shall furnish the CONTRACTING AUTHORITY with an original copy of an insurance policy issued for the benefit of the CONTRACTING AUTHORITY or which specifies the CONTRACTING AUTHORITY as a third benefit recipient /beneficiary.

- The Performance Guarantee shall be in an amount equal to 5% of the Contract Price.

- The amount of the Performance Guarantee shall be subject to adjustment in proportion to any adjustment of the Contract Price under this Agreement.  The CONTRACTOR shall promptly upon such adjustment and at its own expense arrange for submission to the CONTRACTING AUTHORITY of a revised Performance Guarantee each time when the Contract Price is adjusted, whether by way of increase or decrease, and this adjustment equals or exceeds Euro 50,000 (fifty thousand)

- If the CONTRACTOR shall fail to provide any revised Performance Guarantee in accordance with paragraph (d) above then the CONTRACTING AUTHORITY may retain the amount which would otherwise have been included in such revised Performance Guarantee from any payment which may subsequently become due to the CONTRACTOR.

- The Performance Guarantee shall be effective and operative throughout the entire contract period plus 30 (thirty) days after Contract completion.

- Any costs related to the signing of the bank guarantee or the insurance contract and maintaining their effectiveness for the required period, as well as to any payment of fees, insurance compensation for the benefit of the CONTRACTING AUTHORITY or any other expenses, shall be at the CONTRACTOR’s expense.

# 19	Insurance

19.1	The CONTRACTOR shall provide and maintain in full force and effect throughout the term of the Agreement, at the CONTRACTOR’s expense, the following insurance coverage:

(a) 	Worker’s Compensation: To the extent required by Applicable Laws, the CONTRACTOR shall maintain at all times worker’s compensation insurance with the statutory limits and coverage as required. Additionally, the CONTRACTOR will provide Employers Liability coverage in the amount of 200,000 Euros each occurrence and 200,000 Euros in aggregate;

(b) 	Third Party Liability: The CONTRACTOR shall maintain third party liability insurance including products and completed operations, contractual liability and sudden and accidental pollution with not less than 2,500,000 Euro limit per occurrence.

19.2	The CONTRACTOR shall provide to the CONTRACTING AUTHORITY evidence of the CONTRACTOR’s general liability insurance for the term of this Agreement. The CONTRACTOR shall provide all information reasonably requested by the CONTRACTING AUTHORITY for the purposes of the CONTRACTING AUTHORITY’s insurance policies relevant to the Works.

# 20	Applicable Laws, Approvals and Other Requirements

20.1	The CONTRACTOR undertakes that in the performance of this Agreement, it shall comply with, and it shall cause each of its SUBCONTRACTORS to comply with (a) all Applicable Laws and Approvals in force throughout the term of the Agreement and (b) all of the CONTRACTING AUTHORITY’s obligations under agreements relating to the Facility insofar as such obligations relate to the Works, and furthermore shall ensure that the Works comply with each of the foregoing. Notwithstanding any other provision of this Agreement, the CONTRACTOR shall indemnify the CONTRACTING AUTHORITY against any breach of the above undertaking. The CONTRACTOR is deemed to have made full allowance in the Contract Price for the cost of complying with all Applicable Laws and Approvals which were in force (including those published but not yet in force) on the date of signature of this Agreement and to have fully ascertained the manner in which said Applicable Laws and Approvals affect the execution of the Works and the performance of the Agreement.

20.2	The CONTRACTING AUTHORITY shall be responsible for obtaining the Approvals necessary for the Works in their permanent form. The CONTRACTOR shall be responsible for obtaining all other Approvals as may be necessary in connection with the execution of the Works as required by Bulgarian law.

20.3	If the cost to the CONTRACTOR of performing his obligations under this Agreement shall be increased or reduced by the making or amendment after the date of this Agreement of any Applicable Law, the amount of such increase or reduction (to the extent that it arises directly in the carrying out of the Works) shall be added to or deducted from the Contract Price as the case may be.

# 21	CONTRACTOR’s Events of Default

21.1	If the CONTRACTOR:

(a)	fails to proceed with the Works with due care and diligence after being required in writing by the CONTRACTING AUTHORITY to do so within 30 days term and in accordance with this Agreement; or

(b)	fails to execute the Works or to perform his obligations in accordance with this Agreement after being required by the CONTRACTING AUTHORITY in writing to do so within 30 days term;  or

(c)	fails to comply with any reasonable orders given to him in writing within 14 days term by the CONTRACTING AUTHORITY and in accordance with this Agreement; or

(d)	refuses or neglects to remove defective materials or make good defective work after being directed by the CONTRACTING AUTHORITY in writing to do so within 14 days term; or

(e) 	fails to Complete the Works on  Longstop Completion Date and all the additional time given by the CONTRACTING AUTHORITY to the CONTRACTOR as per Clause 14.5 of this Agreement expires; or

(f)	is declared bankrupt or goes into liquidation procedure

then in such event and without prejudice to any other rights or remedies, the CONTRACTING AUTHORITY may by 15 days’ written notice to the CONTRACTOR forthwith terminate this Agreement (for avoidance of doubt the CONTRACTING AUTHORITY cannot terminate the Contract in case the CONTRACTOR cures the breach before the expiration of the 15 days notice period referred above) and thereupon the CONTRACTING AUTHORITY may take possession of all materials belonging to the scope of Works, and other things whatsoever brought on to the Site or manufactured for the Works and ready for shipment or are in transit to be delivered to the Site by the CONTRACTOR and requires that all the Sub-contracts are assigned to him and may use them for the purposes of executing, completing and maintaining the Works.

21.2	The CONTRACTOR shall allow or pay to the CONTRACTING AUTHORITY the amount of any direct loss or damage caused to the CONTRACTING AUTHORITY by reason of such termination and for any excess cost incurred by the CONTRACTING AUTHORITY in completing the Works by himself or by third party.

21.3	Upon receipt of the CONTRACTOR’s application for payment following termination pursuant to Clause 21.1 accompanied by supporting details, the CONTRACTING AUTHORITY shall ascertain the sums due to the CONTRACTOR up to the date of termination.  Such sums shall include the value of work completed and the amount of any expenditure reasonably incurred by the CONTRACTOR in expectation of the performance of the Agreement.  Thereafter the CONTRACTING AUTHORITY shall issue a certificate of payment for the amount by which the termination value of the Works exceeds, if applicable, the total of sums previously paid to the CONTRACTOR and such certificate of payment shall be paid by the CONTRACTING AUTHORITY within 30 days after the date of issue.

# 22	CONTRACTING AUTHORITY’s Events of Default

22.1	If the CONTRACTING AUTHORITY:

(a)	fails to make any undisputed payment amounting to at least [EUR/BGN] properly due and owing to the CONTRACTOR; or

(b)	commits a material breach of this Agreement and fails to remedy such breach within 30 days of the date on which the CONTRACTOR provides written notice to the CONTRACTING AUTHORITY alleging such breach;

then in such event and without prejudice to any other rights or remedies, the CONTRACTOR shall be entitled to immediately suspend the performance of the Works and if the CONTRACTING AUTHORITY has not cured the failure to make payment or the material breach within 30 days of such suspension the CONTRACTOR shall be entitled to terminate this Agreement by 15 days notice to the CONTRACTING AUTHORITY. For avoidance of doubt the CONTRACTOR cannot terminate the Contract in case the CONTRACTING AUTHORITY cures the breach before the expiration of the 15 days notice period referred above.

  - If the CONTRACTING AUTHORITY is declared bankrupt or goes into liquidation procedure the CONTRACTOR shall be entitled to immediately terminate this Agreement.

22.3 	For purposes of this Clause 22 “suspend” shall mean the CONTRACTOR and any SUBCONTRACTOR shall immediately be entitled to cease the performance of the Works provided the CONTRACTOR first stores, preserves, protects and otherwise secures the affected Works in accordance with Good Industry Practice.  Provided the CONTRACTOR decides not to terminate the Contract he shall be entitled to be reimbursed for the reasonable costs incurred as direct result of this suspension.

22.4	Upon termination in accordance to this Clause 22 the CONTRACTING AUTHORITY shall certify and pay to the CONTRACTOR all sums due at the date of termination, breaking fees, as well as shall reimburse the CONTRACTOR for all reasonable costs, incurred by the CONTRACTOR as a direct result of the suspension as per 22.3 above, which are not paid at the time of the termination and shall return the Advance Payment Guarantee and Performance Guarantee within 30 days from the date of termination. The CONTRACTING AUTHORITY shall, on the application of the CONTRACTOR, accompanied by supporting details, also certify and pay to the CONTRACTOR the amount of any expenditure reasonably incurred by the CONTRACTOR in expectation of the performance of, or in consequence of the termination of the Contract.

# 23	Liability and Limitations on Liability

23.1 	In no circumstances whatsoever other than in the case of any liability of the CONTRACTOR to indemnify the CONTRACTING AUTHORITY against claims by third parties pursuant to Clauses 23.3, shall the liability of the CONTRACTOR to the CONTRACTING AUTHORITY under this Agreement exceed the Contract Price.

23.2	The aggregate of any liquidated damages payable by the CONTRACTOR pursuant to Clause 14.4 shall not exceed the 20 % of the Contract Price.

23.3 	The CONTRACTOR agrees to defend, indemnify and hold harmless the CONTRACTING AUTHORITY from and against any and all claims, losses, liabilities, costs and reasonable expenses for personal injury or death to persons or damage to property caused to or suffered by the CONTRACTING AUTHORITY (or any of its employees, officers, directors, agents, CONTRACTORS and SUBCONTRACTORS) or any third party arising out of any act or omission of the CONTRACTOR (or of any SUBCONTRACTOR acting on its behalf) or the default by the CONTRACTOR of its obligations under this Agreement.

23.4 	The CONTRACTOR shall be responsible for and shall indemnify the CONTRACTING AUTHORITY for the cost of making good any property loss or damage to any part of the Facility arising out of or in connection with the performance of the Works.

# 24	Confidentiality

24.1	The CONTRACTOR shall not communicate or use in advertising, publicity, sales release or in any other medium, photographs or other reproduction of the Works which are the subject of this Agreement, or description of the Site, dimensions, quantity, quality or other information concerning the Works or the Facility except with the prior written permission of the CONTRACTING AUTHORITY and subject to such conditions as the CONTRACTING AUTHORITY may prescribe.

24.2	Throughout the term of this Agreement and at any time thereafter the CONTRACTOR shall treat this Agreement and all information obtained thereunder as confidential and the same shall not be divulged by the CONTRACTOR, its servants or agents to any third party except to the extent necessary for the performance of this Agreement and then only on the basis that such third party shall be bound by similar confidentiality obligations as detailed herein.

24.3	The provisions of this Clause shall not apply to any such information which:

(a) 	is, or shall become, part of the public domain otherwise than in consequence of a breach by the CONTRACTOR of his obligations under this Clause, or

(b)	was in the CONTRACTOR's possession (with full rights to disclose) prior to receipt from the CONTRACTING AUTHORITY, or

(c) 	was received by the CONTRACTOR from a third party who has the right to divulge such information to any third party, or

(d) 	the CONTRACTOR is required to disclose pursuant to any Applicable Law or the direction of any court.

# 25	Assignment and Sub-Contracting

25.1	The CONTRACTOR shall not without the written consent of the CONTRACTING AUTHORITY assign all or any portion of this Agreement or any of his obligations under this Agreement. The CONTRACTOR gives its express consent that the Subcontract Agreements with the Subcontractos listed in Schedule B and the contracts referred to in 25.3 below are assigned to the CONTRACTING AUTHORITY provided this Agreement is terminated due to CONTRACTOR’s event of default. The CONTRACTOR hereby authorizes the CONTRACTING AUTHORITY, not later than 7 business days after the date of termination, to give notice to the SUBCONTRACTOR for such assignment subject to the occurrence of termination of this Contract due to CONTRACTOR’s event of Default.

25.2 The CONTRACTING AUTHORITY may grant a charge, mortgage, assignment by way of security or other encumbrance over this Agreement or its rights and benefits therein to any person providing financing or refinancing for the Facility.

25.3 Except as provided in this Clause 25.3, the CONTRACTOR shall not sub-contract or procure any part of the Works without the prior consent of the CONTRACTING AUTHORITY. Notwithstanding any approval or otherwise of any SUBCONTRACTOR by the CONTRACTING AUTHORITY the CONTRACTOR shall be responsible for the acts, defaults and neglects of any SUBCONTRACTOR, his agents, servants or workmen as fully as if they were the acts, defaults or neglects of the CONTRACTOR, his agents, servants or workmen.

25.4	This Agreement shall be binding on the parties and their respective successors and permitted assigns.

# 26	Law, Jurisdiction, Disputes and Language

26.1	This Agreement shall be construed in accordance with and governed by the laws of Bulgaria.

26.2	If any term or provision in this Agreement shall be held to be illegal or unenforceable, in whole or in part, under any enactment or rule of law, such term or provision or part shall to that extent be deemed not to form part of this Agreement but the validity and enforceability of the remainder of this Agreement shall not be affected.

26.3	In the event that any dispute shall arise in connection with the performance of this Agreement which cannot be resolved amicably at working level then such dispute shall be referred to a Management Committee (as hereafter defined) by either party giving notice in writing to the other.  The Management Committee shall comprise one senior representative from each party, whose purpose is to review and decide upon all matters related to unresolved disputes.  In the event of failure of the senior representatives to resolve such dispute within thirty (30) days of such referral being made then either party may refer the dispute to such Dispute a to binding arbitration for final settlement. The arbitration shall be conducted by a single arbitrator or, upon the failure of the parties to agree upon a single arbitrator within 15 days of receipt by respondent of the notice of arbitration, by three arbitrators, one appointed by each Party within 30 days of receipt by respondent of the notice of arbitration and a third appointed by the two arbitrators appointed by the parties within 30 days of the appointment of the second arbitrator. The arbitration shall be conducted under the Arbitration Rules (the "Rules") of UNCITRAL, The third arbitrator shall not be a citizen, national or resident of Bulgaria, Croatia, Austria or Germany. If any arbitrator has not been appointed within the time limits specified herein or in the Rules, upon the written request of either party such appointment shall be made by the International Court of Arbitration of the ICC, which shall act as appointing authority.  The arbitration shall be conducted and the award shall be rendered in the English language. The place of arbitration shall be Geneva, Switzerland.  The arbitration proceeding and any award rendered thereunder shall be governed by the laws of Switzerland and the United Nations Convention on the Recognition and Enforcement of Foreign Arbitral Awards, 1958. The Parties to the proceeding or their designated representatives shall have the right to cross-examine witnesses during the arbitral proceeding.  The Parties agree that the arbitrator(s) shall also determine and make an award as to the allocation of the costs of the arbitration proceeding including reasonable attorneys fees.

26.4	If a third party makes a claim against the CONTRACTING AUTHORITY arising from the performance of this Agreement by the CONTRACTOR, or in respect of goods or services supplied under it, the CONTRACTOR shall at its own expense on request by the CONTRACTING AUTHORITY join the CONTRACTING AUTHORITY in defending the claim.  The decision of any court or arbitration tribunal deciding upon the claim shall, so far as is relevant, be admitted as conclusive in any consequent claim by the CONTRACTING AUTHORITY or against the CONTRACTOR under this Agreement.

26.5	Performance of this Agreement shall continue during any dispute, court or arbitral   proceedings unless the CONTRACTING AUTHORITY shall order the suspension thereof.

26.6	The language of communication shall be English. All statutory documents shall be issued in Bulgarian with translations into English.

26.7	The language of this Agreement shall be English.

# 27	Force Majeure

Upon the occurrence of, and during the continuance of, a Force Majeure event and the effects thereof, the affected party shall not be liable for any failure or delay in performing its obligations under or pursuant to this Agreement, but only to the extent affected by such Force Majeure.  The affected party shall use all reasonable endeavours to mitigate the adverse effects of such Force Majeure.  For purposes of this Agreement, “Force Majeure” means any event or circumstance or combination of events or circumstances beyond the reasonable control of the affected party and which (or the effects of which) materially and adversely affect the ability of that party to perform its obligations under or pursuant to this Agreement.

## 27.1	Notification Obligations

If by reason of a Force Majeure Event a party is wholly or partially unable to carry out its obligations under this Agreement, the affected Party shall:

- give the other party notice of the Force Majeure Event(s) as soon as reasonably practicable, but in any event, not later than the later of forty-eight (48) hours after the affected party becomes aware of the occurrence of the Force Majeure Event(s) and twelve (12) hours after the resumption of any means of providing notice between the parties.  When appropriate or when reasonably requested to do so by the other party, the affected party shall provide further notices to the other party more fully describing the Force Majeure Event(s) and its cause(s) and providing or updating information relating to the efforts of the affected party to avoid and/or to mitigate the effect(s) thereof and estimates, to the extent practicable, of the time that the affected party reasonably expects it will be unable to carry out any of its affected obligations due to the Force Majeure Event(s); and

- give notice to the other party of the cessation of the Force Majeure Event, and the affected party's ability to recommence performance of its obligations under this Agreement by reason of the cessation of the Force Majeure Event.

Failure by the affected party to give notice of a Force Majeure Event to the other party within the period required by this Article 27.1 shall not prevent the affected party from giving such notice at a later time; provided, however, that the affected party shall not be excused pursuant to Article 27.1 prior to the giving of the required notice.

## 27.2	 Duty to Mitigate

The affected party shall use all reasonable efforts:

- to minimise the duration of a Force Majeure Event and to mitigate the effects of a Force Majeure Event including, but not limited to, the payment of all reasonable sums of money by or on behalf of the affected party, which sums are reasonable in light of the likely success of the mitigation measures;

- ensure prompt resumption of normal performance of this Agreement after cessation of the Force Majeure Event.

## 27.3	Effect of Extended Force Majeure Event

If a Force Majeure Event delays the performance of the obligations of the affected Party for more than four months (an "Extended Force Majeure Event"), the other Party may terminate this Agreement.

## 27.4	Effect of the Termination

Upon termination pursuant to Clause 27.3 the Parties shall use all reasonable efforts to settle the consequences of the termination as fair as possible to the satisfaction of both Parties. The CONTRACTING AUTHORITY shall ascertain the sums due to the CONTRACTOR up to the date of termination, which sums shall include the value of work completed and the amount of any expenditure reasonably incurred by the CONTRACTOR in expectation of the performance of the Agreement and such certificate of payment shall be paid by the CONTRACTING AUTHORITY within 30 days after the date of issue.

# Health & Safety

The CONTRACTING AUTHORITY shall be entitled by notice to the CONTRACTOR to object to any representative or person employed by the CONTRACTOR in the performance of or otherwise about the Scope who has violated the health and safety, environmental and security rules of the CONTRACTING AUTHORITY. CONTRACTOR will either insure that such representative or person will comply with the health and safety, environmental and security rules or remove such representative or person from the CONTRACTING AUTHORITY’s premises.

CONTRACTOR’s Work does not comprise the use of special protective and preventive measures against any health or safety risks for CONTRACTOR’s and its SUBCONTRACTORs’ personnel in or arising out of CONTRACTING AUTHORITY’s plant or equipment or existing on CONTRACTING AUTHORITY site to the extent such measures go beyond what is normal and usual for the type of work to be performed by CONTRACTOR. However, CONTRACTOR shall be responsible for any health or safety risk to the extent this has been created due to his fault.

In the given case of health or safety risks for which CONTRACTOR is not responsible as defined in the two preceding sentences above (including but not limited to the asbestos concentrations in the work area or an area used for access to the work area are greater than 1,000 particles / m3 of ambient air) (hereinafter referred to as “Health or Safety Risks”) the Parties shall reach agreement in good faith how to proceed, based on the definitions of SCHEDULE L. Any increase in costs arising out of this shall be for the CONTRACTING AUTHORITY’s account and ,if necessary, the duration of the Outage will be extended as necessary.

However, CONTRACTOR shall not be obligated to carry out any Work at all if the asbestos concentration exceeds 100,000 particles / m3 ambient air.

In case of substantiated doubt regarding the existence of CONTRACTING AUTHORITY Health or Safety Risks the CONTRACTING AUTHORITY shall provide proof of their non-existence by means of an expertise of an independent, internationally operating, specialized and qualified company or institute agreed upon by the Parties. The expertise shall take into account all circumstances including but not limited to the environment of the Site. Nothing in this Contract shall in any way be construed to limit CONTRACTOR, in its sole discretion, from taking any samples or measurements of such areas, though CONTRACTOR shall have no obligation to do so.

In the event there are CONTRACTING AUTHORITY Health or Safety Risks or there exists any substantiated doubt that the same exist or may be created by or during the Work, or the CONTRACTING AUTHORITY has failed to comply with any of its obligations set out in the preceding paragraphs, then, without limiting its other rights and remedies, CONTRACTOR shall be entitled to suspend its Work until (a) the respective CONTRACTING AUTHORITY Health or Safety Risk has been permanently eliminated, or (b) the addressed (substantiated) doubt has been proven to be unsubstantiated, or (c) agreed protective and preventive measures have been taken.

CONTRACTING AUTHORITY shall indemnify and hold CONTRACTOR harmless from and against any claims, losses or damages any employee of CONTRACTOR or its SUBCONTRACTORS or any other third party may demand from CONTRACTOR and arising out of the realization of any CONTRACTING AUTHORITY Health or Safety Risks or the disposal of any waste CONTRACTING AUTHORITY is responsible for.

# 29 	Waiver

29.1	Without prejudice to the provisions of Clause 15 any substitution, deletion, or modification of, or addition to, any term, provision or condition of this Agreement, whether by notation on the Agreement or by separate letter, shall not be valid unless specifically agreed in writing by a duly authorised officer or representative on behalf of each party.

29.2	Any waiver by the CONTRACTING AUTHORITY or its nominated representative (whether with or without knowledge, and whether in whole or in part) of any term, provision or condition of this Agreement shall not constitute a precedent, nor bind the CONTRACTING AUTHORITY, to a waiver in respect of any of the same, or any other term, provision or condition of this Agreement.

# 30	Notices

All notices required to be issued in connection with this Agreement shall be in writing and shall be considered to be served if either delivered by hand, or if receipt of the same by facsimile transmission or recorded delivery registered post at the address of the recipient party stated below, can be reasonably demonstrated.

For the CONTRACTOR: -

……………………..

Original marked  “For the attention of the CONTRACTOR’s Representative”

For the CONTRACTING AUTHORITY:-

CONTOURGLOBAL MARITSA EAST 3 AD

48, Sitnyakovo Blvd, 9th fl.

Sofia 1505

Bulgaria

Telephone: +359 2 8102323

Fax: +359 2 8102345

Original marked “For the attention of the CONTRACTING AUTHORITY’s Representative”

# 31	Entire Agreement

This Agreement and the documents referred to in it contain the whole agreement between the parties relating to the subject matter of this Agreement and supersede all previous agreements (whether oral or written) relating to that subject matter.

# 32	Amendments

No amendment, modification or supplement to this Agreement shall be binding on the parties unless in writing and signed on behalf of each of the parties.

# 33	Ancillary provisions

33.1	The Parties acknowledge that in conducting their business and managing their internal relations, both the CONTRACTING AUTHORITY and the CONTRACTOR operate by eference to the principles contained in the CONTRACTING AUTHORITY’s Anticorruption Policy – Schedule H, the Supplier Code of Conduct – Schedule I and Vendor Certificate – Sanctions Laws – Schedule J. The Parties shall not engage in any conduct that would constitute a breach of these Policies or would result in a breach of these Policies.  The Parties agree that, with respect to the services provided under any agreement, whether written or otherwise, neither it nor any of its principals, employees, affiliates, or to its knowledge, agents or representatives will directly or indirectly, make, promise or authorize the making of any offer, gift or payment of anything of value, including without limitation, the sharing or promise to share its fees or any other funds that it has received, receives or will receive under any agreement with ContourGlobal, to or for the benefit of any Government Official or family member or close business associate of any Government Official, for the purpose of improperly: (i) influencing any act or decision of the Government Official in his or her official capacity; (ii) inducing the Government Official to do or omit to do any act in violation of his or her lawful duty; (iii) securing any improper advantage; or (iv) inducing the Government Official to use his or her influence to affect any governmental act or decision (any of the foregoing a “Prohibited Payment”).   The Parties shall promptly report to the other any Prohibited Payment.

33.2	By signing this Agreement, the CONTRACTOR declares that he is familiar with the company policy of the CONTRACTING AUTHORITY with regard to the CONTRACTING AUTHORITY disagreeing with the possible transfer of the takings under (reassignment of) the public procurement contract, and consequently all notifications to him in this respect will fail to produce legal effect.

IN WITNESS WHEREOF the parties have entered into this Agreement as of the day and year first before written.

For and on behalf of

CONTOURGLOBAL MARITSA EAST III AD

…………………………………………………….

Krassimir Nenov

Executive Director

…………………………………………………….

Quinto Di Ferdinando

Member of the Board of Directors

For and on behalf of

………………